## Sheet1
Streetlight Repair Program 2010
|  | POLES TO BE REPLACED | STREETLIGHT POLES TO BE REPLACED
Pole | Agency | StreetlightNumber | StreetlightNumberInField | Address | Street | CrossStreet | PoleType | PoleLat | PoleLon | DebrisAtBase | PolePaint | PoleRust | PoleLean | PoleDamage | FixtureMissing | FixtureQty | FixturePaint | FixtureRust | FixtureLean | FixtureDamage | FixtureCxnBad | ArmPaint | ArmRust | ArmLean | ArmDamage | ArmCxnBad | CleanAndPaint | PhysicalTest | ClearDebris | BuildRetainingWall | ReplacePole | ReplaceArm | ReplaceFixture | RemoveMetricom | Priority | Comments | InspectionDate | InspectorID | Inspector | LampType | Service | FixtureType | Suspension | HHC | HHCType | PoleNumberMissing | DigitMissing | HasPhoto | LensDamage | Knocked down | Voltage | PoleUse | PoleLength | Notes | Price
14673 | BEL MARIN KEYS C.S.D. | 5U | 5U | 109 | MONTEGO KEY |  | Wood-Standard | 38.0861 | -122.526 |  |  |  | Significant |  |  | 1 | [20 empty] | 40098.4253 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
14696 | BELVEDERE, TOWN OF | 7Z | 7Z |  | BAY VIEW AV | TOYON AV | Wood-Standard | 37.872 | -122.4646 |  |  |  | Significant |  |  | 1 | [20 empty] | 40102.4172 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
151717 | LARKSPUR | NULL | 1225f |  | SIR FRANCIS DRAKE BLVD | LARKSPUR LANDING CIR | Metal | 37.9456 | -122.5119 |  |  |  | Slight | Dented-Major |  | 2 | [20 empty] | 40093.4734 | 442 | Chris C | HPS 200W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | #N/A | #N/A | Needs new Pole (Ameron) - Foundation ok | 4500
14885 | MARIN CENTER | 531A | 531A |  | FAIRGROUNDS |  | Metal | 38.002 | -122.5338 |  | Peeling/Cracked |  | Significant |  |  | 1 | Faded |  |  | Dented-Minor | [16 empty] | 40128.587 | 452 | Mike Gomer | HPS 70W | Underground | Hat | Post Top | [7 empty] | 240 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' | Dig around foundation & Straighten | 1400
16555 | MARIN, COUNTY OF | 3569A | 3569A |  | POINT SAN PEDRO RD | MONTECITO RD 600' NE/O | Metal | 37.9715 | -122.5006 |  |  |  |  | Dented-Major |  | 2 | [20 empty] | 40133.5542 | 452 | Mike Gomer | HPS 100W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 35' to 39' | PG&E - N/A
16341 | MARIN, COUNTY OF | 58G | 58G | 538 | TAMALPAIS DR |  | Wood-Standard | 37.9006 | -122.5562 |  |  |  | Significant |  |  | 1 | [20 empty] | 40156.6061 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
15937 | MARIN, COUNTY OF | 62G | 62G | 207 | MELROSE AV | EVERGREEN AV | Wood-Standard | 37.8963 | -122.5432 |  |  |  | Significant |  |  | 1 | [20 empty] | 40120.6196 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
18270 | MILL VALLEY | 540H | 540H | 32 | DELL LN |  | Wood-Standard | 37.9057 | -122.5423 |  |  |  |  | Cracked-Major |  | 1 | [11 empty] | 1 | [7 empty] | pole is rotting | 40106.4104 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
18931 | NOVATO | 1322J | 1322J |  | BAHIA DR | CERRO CREST DR 2300' W/O | Metal | 38.1222 | -122.5393 |  |  |  |  | Dented-Major |  | 1 | [19 empty] | missing hhc | 40098.5638 | 452 | Mike Gomer | HPS 100W | Underground | Cobra | Mast Arm | missing | [6 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
30342 | NOVATO | 3178J | 3178J |  | MAIN GATE RD | NAVE DR | Metal | 38.0559 | -122.528 |  | Faded |  |  | Dented-Major |  | 1 | [5 empty] | Faded | [14 empty] | 40087.4209 | 452 | Mike Gomer | HPS 150W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 30' to 34' | Non-Standard (Similar to Type 15) - Foundation ok | 2900
20430 | NOVATO | 1518J | 1518J | 50 | ROBINHOOD DR |  | Wood-Center Bore | 38.1087 | -122.5498 | [6 empty] | 1 | [8 empty] | Cracked-Major | [6 empty] | 1 |  |  |  |  | 40074.4341 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 35' to 39' | 30-ft wood center bore - rotted out by wood-peckers | 3300
18928 | NOVATO | 1341J | 1341J |  | BAHIA DR | TOPAZ DR | Wood-Center Bore | 38.1256 | -122.5298 | [6 empty] | 1 | [20 empty] | 40098.5542 | 452 | Mike Gomer | HPS 100W | Underground | Cobra | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Pole Missing (knocked down 7/3/10) - 30-ft wood center bore | 3500
26356 | NOVATO | 80N | 80N | MEDIAN W | REDWOOD BLVD S/B | VALLEJO AV S/O | Wood-Center Bore | 38.1086 | -122.57 | [6 empty] | 1 | [20 empty] | 40066.315 | 107 | Don C | HPS 70W | Underground | Shoebox | Soffit | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' | 16-ft Laminate Wood Pole is Rotten and loose | 2800
22039 | SAN RAFAEL | SR84 | SR84 | 110 | BAY WY |  | Concrete | 37.9717 | -122.4923 |  |  |  |  | Cracked-Major |  | 1 | [18 empty] | 3 | base of pole broken | 40108.4245 | 442 | Chris C | HPS 70W | Underground | Hat | Post Top | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 20' to 24' | 20-ft Marbelite - Direct Burial - Broken at bottom | 4400
21905 | SAN RAFAEL | 471 | 471 |  | LOOTENS PL | CIJOS ST, ALLEY BETWEEN | Metal | 37.9724 | -122.5254 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40133.4868 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Mast Arm | damaged | Dual-Large | [5 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Needs new Type 15 pole w/ 6-ft arm. Foundation ok. | 3200
22369 | SAN RAFAEL | 646 | 646 | ALLEY | CIJOS ST |  | Metal | 37.9724 | -122.5251 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40135.4242 | 452 | Mike Gomer | HPS 200W | Underground | Cobra | Mast Arm | damaged | Dual-Large | [5 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Needs new Type 15 pole w/ 6-ft arm. Foundation ok. | 3200
24730 | SAN RAFAEL | 2815 | 2815 | SAFETY LIGHT | 2ND ST | GRAND AV, SWC | Metal | 37.9702 | -122.519 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40135.5865 | 452 | Mike Gomer | HPS 200W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 20' to 24' | Needs new Pole - Type 15 w/ 12-ft arm - Foundation ok | 4600
24989 | SAN RAFAEL | 2817 | 2817 |  | 3RD ST | EMBARCADERO WY | Metal | 37.9688 | -122.5119 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40133.5986 | 452 | Mike Gomer | HPS 100W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
24676 | SAN RAFAEL | 2825 | 2825 | 13 | POINT SAN PEDRO RD |  | Metal | 37.9681 | -122.5098 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40133.5954 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
24675 | SAN RAFAEL | 2826 | 2826 | 13 | POINT SAN PEDRO RD |  | Metal | 37.9681 | -122.5098 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40133.549 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
21833 | SAN RAFAEL | 3062 | 3062 |  | 5TH AV | A ST A/F | Metal | 37.9742 | -122.5282 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40130.4935 | 452 | Mike Gomer | HPS 200W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Needs new Type 15 pole (only). Foundation ok. | 2900
23837 | SAN RAFAEL | 3330 | 3330 |  | MANUEL T FREITAS PKWY | SYLVIA WY | Metal | 38.0095 | -122.5659 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40101.4838 | 442 | Chris C | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Type 15D (2 fixtures) - Needs new Pole (only) - Foundation ok | 3500
23838 | SAN RAFAEL | 3331 | 3331 |  | MANUEL T FREITAS PKWY | SYLVIA WY | Metal | 38.0096 | -122.5659 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40101.4824 | 442 | Chris C | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29'
28825 | SAN RAFAEL | 4480 | 4480 |  | ANDERSEN DR | FRANCISCO BLVD W 350' S/O | Metal | 37.9594 | -122.5106 |  |  |  |  | Dented-Major |  | 1 | [20 empty] | 40134.5345 | 452 | Mike Gomer | HPS 250W | Underground | Cobra | Mast Arm | [7 empty] | 240 V | NULL | 30' to 34' | Needs new Type 15 pole (only). Foundation ok. | 2900
21957 | SAN RAFAEL | 3383 | 3383 | 1261 | ANDERSEN DR |  | Metal | 37.9515 | -122.4984 |  |  |  | Significant |  |  | 1 | [20 empty] | 40134.559 | 452 | Mike Gomer | HPS 100W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 35' to 39' | Straighten Type 15 Direct Burial | 1400
21958 | SAN RAFAEL | 3385 | 3385 | 1281 | ANDERSEN DR |  | Metal | 37.9509 | -122.4976 |  |  |  |  | Dented-Minor |  | 1 | [20 empty] | 40134.5583 | 452 | Mike Gomer | HPS 100W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 35' to 39' | Straighten Type 15 Direct Burial | 1400
25441 | SAUSALITO | 720Y | 720Y | 2631 | BRIDGEWAY | @COLOMA ST NW/O | Metal | 37.8687 | -122.5027 |  |  |  |  | Dented-Major |  | 2 | [19 empty] | missing # | 40128.3879 | 452 | Mike Gomer | HPS 100W | Underground | Cobra | Mast Arm |  |  | 1 |  |  |  |  | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 30' to 34' | Type 15D - Needs new Pole (only) - Foundation ok | 2900
25847 | SAUSALITO | 580Y | 580Y | 300 | NAPA ST | SAUSALITO CRUISE CLUB | Wood-Standard | 37.8616 | -122.4887 |  |  |  | Significant |  |  | 1 | [20 empty] | 40165.3878 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm |  |  | 1 | 1 |  |  |  | 240 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | PG&E - N/A
25684 | SAUSALITO | 682Y | 682Y | 14 | JOSEPHINE ST |  | Metal | 37.8512 | -122.4799 |  |  |  | Significant |  |  | 1 | [11 empty] | 1 | [8 empty] | 40127.3741 | 452 | Mike Gomer | MV 175W | Underground | Hat | Post Top | [7 empty] | 240 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' | Needs new foundation | 5200
25998 | TIBURON | 71T | 71T | 442 | GREENWOOD BEACH RD |  | Wood-Standard | 37.8955 | -122.492 |  |  |  | Significant |  |  | 1 | [20 empty] | 40099.4063 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 40' | PG&E - N/A
[54 empty] | SubTotal Poles ( 16 EA) | 54000
|  | FIXTURES TO BE REPLACED | ARMS TO BE REPLACED
26806 | CORTE MADERA, TOWN OF | 377B | 377B |  | PRINCE ROYAL DR | MARINER GREEN | Metal | 37.9173 | -122.5031 | [5 empty] | 1 | 1 | [8 empty] | broken off | [6 empty] | 1 | 1 |  | 2 | mast arm appears to have been broken off. construction happening across street | 40074.4805 | 442 | Chris C | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | NULL | 20' to 24' | Replace Arm (Broken Off) | 400
15672 | MARIN, COUNTY OF | 186J | 186J | 137 | HILLSIDE AV |  | Wood-Standard | 37.9561 | -122.5548 | [5 empty] | 1 | 1 | [15 empty] | 1 | 1 |  |  | label on pole, no mast arm or fixture. appears to have no electric hookup either | 40094.6138 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Replace Arm (Missing) | 400
15962 | MARIN, COUNTY OF | 3400W | 3400W | 68 | MILLAND DR |  | Wood-Center Bore | 37.894 | -122.5133 | [6 empty] | 1 | [7 empty] | Slight | Cracked-Major | [6 empty] | 1 |  |  |  |  | 40102.4642 | 452 | Mike Gomer | HPS 70W | Underground | Lantern | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 20' to 24' | Cracked Arm | 400
19419 | NOVATO | 2114J | 2114J |  | ESCALLONIA DR | REDWOOD BLVD 800' W/O | Wood-Center Bore | 38.1163 | -122.5701 | [6 empty] | 1 |  |  | Significant |  |  |  |  | Significant | [7 empty] | 1 |  |  | 2 |  | 40073.3265 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 30' to 34' | Significant Lean | 400
[54 empty] | SubTotal Arms (4 EA) | 1600
|  | FIXTURES TO BE REPLACED | FIXTURES TO BE REPLACED
Pole | Agency | StreetlightNumber | StreetlightNumberInField | Address | Street | CrossStreet | PoleType | PoleLat | PoleLon | DebrisAtBase | PolePaint | PoleRust | PoleLean | PoleDamage | FixtureMissing | FixtureQty | FixturePaint | FixtureRust | FixtureLean | FixtureDamage | FixtureCxnBad | ArmPaint | ArmRust | ArmLean | ArmDamage | ArmCxnBad | CleanAndPaint | PhysicalTest | ClearDebris | BuildRetainingWall | ReplacePole | ReplaceArm | ReplaceFixture | RemoveMetricom | Priority | Comments | InspectionDate | InspectorID | Inspector | LampType | Service | FixtureType | Suspension | HHC | HHCType | PoleNumberMissing | DigitMissing | HasPhoto | LensDamage | Knocked down | Voltage | PoleUse | PoleLength
14634 | BEL MARIN KEYS C.S.D. | 2335U | 2335U | 93 A/F | CARIBE ISLE |  | Metal | 38.0805 | -122.5211 | [6 empty] | 1 | [16 empty] | 1 |  |  |  | 40098.3281 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' |  | 250
14758 | BELVEDERE, TOWN OF | 98Z | 98Z | 111 | GOLDEN GATE AVE | CREST RD | Wood-Standard | 37.8724 | -122.469 | [5 empty] | 1 | 1 | [16 empty] | 1 |  |  |  | 40100.5433 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
26806 | CORTE MADERA, TOWN OF | 377B | 377B |  | PRINCE ROYAL DR | MARINER GREEN | Metal | 37.9173 | -122.5031 | [5 empty] | 1 | 1 | [8 empty] | broken off | [6 empty] | 1 | 1 |  | 2 | mast arm appears to have been broken off. construction happening across street | 40074.4805 | 442 | Chris C | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | NULL | 20' to 24' |  | 250
16988 | FAIRFAX | 230C | 230C | 454 A/F | SCENIC RD |  | Wood-Standard | 37.9875 | -122.5994 | [6 empty] | 1 | [16 empty] | 1 |  |  |  | 40091.6071 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
16836 | FAIRFAX | 530C | 530C |  | GLEN DR | WHITE HILL SCHOOL A/F | Metal | 38.0026 | -122.6058 | [6 empty] | 1 | [16 empty] | 1 |  |  |  | 40091.5172 | 442 | Chris C | HPS 70W | Underground | Hat | Post Top | [5 empty] | 1 |  | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' |  | 500
17421 | LARKSPUR | 16F | 16F |  | MADRONE AV | MAGNOLIA AV 200' SW/O | Wood-Standard | 37.9322 | -122.5366 | [6 empty] | 1 | [16 empty] | 1 |  |  | fixture missing lens assembly | 40079.5519 | 442 | Chris C | HPS 200W | Overhead | Cobra | Mast Arm | [7 empty] | 240 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
16309 | MARIN, COUNTY OF | 153R | 153R |  | STARLING RD | STARLING CT | Wood-Standard | 37.8785 | -122.5275 | [5 empty] | 1 | 1 |  |  |  | Cracked-Major | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40119.4349 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
15672 | MARIN, COUNTY OF | 186J | 186J | 137 | HILLSIDE AV |  | Wood-Standard | 37.9561 | -122.5548 | [5 empty] | 1 | 1 | [15 empty] | 1 | 1 |  |  | label on pole, no mast arm or fixture. appears to have no electric hookup either | 40094.6138 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
15850 | MARIN, COUNTY OF | 219J | 219J | 11 | MAKIN GRADE |  | Wood-Standard | 37.9631 | -122.545 | [6 empty] | 1 | [16 empty] | 1 |  |  | lens assembly missing | 40094.408 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
16001 | MARIN, COUNTY OF | 220J | 220J |  | MURRAY AV | FERN RD | Wood-Standard | 37.9429 | -122.5482 | [6 empty] | 1 |  |  |  | missing | [12 empty] | 1 |  |  | door assembly (lens and ballast cover) missing | 40078.526 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
15273 | MARIN, COUNTY OF | 230R | 230R | 825 | AUTUMN LN |  | Wood-Standard | 37.8755 | -122.5462 | [6 empty] | 1 |  |  |  | missing | [12 empty] | 1 |  |  | lamp and bottom half of fixture are missing | 40119.5922 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
15804 | MARIN, COUNTY OF | 3547R | 3547R | 488 | LIVE OAK DR | MARIN AV | Wood-Center Bore | 37.8759 | -122.538 | [6 empty] | 1 |  |  |  | missing | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40119.5601 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 30' to 34' | Sched. 2 - Free | 0
16078 | MARIN, COUNTY OF | 5R | 5R | 188 | LILAC LN |  | Wood-Standard | 37.8863 | -122.5248 | [6 empty] | 1 |  |  |  | Cracked-Major | [12 empty] | 1 |  |  | bottom half of fixture is missing. Pole is also numbered 139r | 40156.6266 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
16059 | MARIN, COUNTY OF | 68R | 68R |  | PINE CREST RD | SHORELINE HWY 1 | Wood-Standard | 37.8838 | -122.5382 | [5 empty] | 1 | 1 |  |  |  | Cracked-Major | [12 empty] | 1 | 1 |  | bottom half of fixture is missing | 40121.4061 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 12' to 15' | Sched. 2 - Free | 0
15208 | MARIN, COUNTY OF | 6R | 6R |  | A ST | 4TH ST | Wood-Standard | 38.0687 | -122.8068 | [5 empty] | 1 | 1 |  |  |  | Cracked-Major | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40121.5493 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 240 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
18655 | MILL VALLEY | 266H | 266H |  | SUMMIT AV | RALSTON AV | Wood-Standard | 37.9128 | -122.5567 | [5 empty] | 1 | 1 |  |  |  | Cracked-Major | [12 empty] | 1 |  |  | missing bottom half of fixture | 40108.423 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
27715 | MILL VALLEY | 978H | 978H |  | UNDERHILL RD | LULA WY | Wood-Center Bore | 37.913 | -122.5189 | [6 empty] | 1 |  |  |  | Cracked-Major | [12 empty] | 1 |  |  |  | 40105.4761 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' |  | 250
19065 | NOVATO | 1117J | 1117J |  | CAIN LN |  | Wood-Center Bore | 38.1067 | -122.5686 | [6 empty] | 1 |  |  |  | Cracked-Minor | [12 empty] | 1 |  |  | wood arm fixture door broken | 40074.5993 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Wood Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free (We will honor these even though Sch. 1 now) | 0
19339 | NOVATO | 1168J | 1168J | 2390 | DOMINIC DR |  | Wood-Standard | 38.1091 | -122.6125 | [5 empty] | 1 | 1 |  |  |  | Cracked-Major | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40078.6136 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free (We will honor these even though Sch. 1 now) | 0
19876 | NOVATO | 2456J | 2456J | 20 | LOVEJOY WY |  | Metal | 38.0575 | -122.5291 | [5 empty] | 1 | 1 |  |  |  | missing | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40087.4423 | 452 | Mike Gomer | HPS 70W | Underground | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free (We will honor these even though Sch. 1 now) | 0
20866 | NOVATO | 816J | 816J | 41 | STASIA DR |  | Wood-Standard | 38.1112 | -122.6164 | [5 empty] | 1 | 1 |  |  |  | missing | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40078.5887 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free (We will honor these even though Sch. 1 now) | 0
19721 | NOVATO | 1624J | 1624J | 1413 | INDIAN VALLEY RD |  | Wood-Standard | 38.0957 | -122.5759 | [6 empty] | 1 |  |  | Significant | [15 empty] | 3 |  | 40084.3892 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free (We will honor these even though Sch. 1 now)
21585 | SAN ANSELMO | 420N | 420N | 123 A/F | SAUNDERS AV | AGATHA CT | Wood-Standard | 37.9805 | -122.5711 | [6 empty] | 1 | [16 empty] | 1 |  |  | missing lens assembly | 40081.5742 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' | Sched. 2 - Free | 0
21506 | SAN ANSELMO | 85N | 85N | 96 | REDWOOD RD |  | Wood-Standard | 37.9779 | -122.5745 | [6 empty] | 1 | [16 empty] | 1 |  |  | lens assembly missing | 40081.5861 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' | Sched. 2 - Free | 0
25123 | SAN RAFAEL | 575 | 575 | 245 | UPPER TOYON DR |  | Wood-Standard | 37.9636 | -122.5398 | [6 empty] | 1 | [16 empty] | 1 |  |  | lens assembly missing | 40094.3723 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
22251 | SAN RAFAEL | 1434 | 1434 | 205 | C ST |  | Wood-Standard | 37.964 | -122.532 | [6 empty] | 1 | [16 empty] | 1 |  |  | lens assembly missing | 40133.3868 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
23098 | SAN RAFAEL | 2198 | 2198 | 18 | GRACELAND DR |  | Wood-Standard | 37.981 | -122.5264 | [6 empty] | 1 | [16 empty] | 1 |  |  | LENS ASSEMBLY MISSING | 40105.3756 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
24798 | SAN RAFAEL | 2638 | 2638 | 32 | SIENNA WY |  | Wood-Standard | 37.9847 | -122.5158 | [6 empty] | 1 | [16 empty] | 1 |  |  |  | 40105.4877 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
24086 | SAN RAFAEL | 3008 | 3008 |  | MONTECILLO RD | KAISER HOSPITAL | Metal | 38.0048 | -122.5542 | [6 empty] | 1 | [16 empty] | 1 |  |  | Lens assembly missing | 40101.6162 | 442 | Chris C | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 25' to 29' |  | 250
23066 | SAN RAFAEL | 3142 | 3142 | 233 | GLEN PARK AV | END | Wood-Standard | 37.9875 | -122.5243 | [6 empty] | 1 | [16 empty] | 1 |  |  | LENS ASSEMBLY MISSING | 40158.6344 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [5 empty] | 1 |  | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
25507 | SAUSALITO | 76Y | 76Y |  | BULKLEY AV | PRINCESS ST | Wood-Standard | 37.8544 | -122.4805 | [5 empty] | 1 | 1 |  |  |  | missing | [12 empty] | 1 |  |  | bottom half of fixture is missing | 40127.3622 | 452 | Mike Gomer | HPS 70W | Overhead | Cobra | Mast Arm | [7 empty] | 120 V | Distribution (Cost of pole will not be included in Replacement Cost) | 25' to 29' |  | 250
25904 | SAUSALITO | 637Y | 637Y | 60 | TOYON LN |  | Metal | 37.858 | -122.4946 |  | Peeling/Cracked |  |  |  |  | 1 |  |  | Significant | [16 empty] | hat is hanging | 40122.5982 | 452 | Mike Gomer | MV 175W | Underground | Hat | Post Top | [7 empty] | 240 V | Street Light Only ( Cost of pole will be included in Replacement Cost) | 12' to 15' |  | 500
[54 empty] | SubTotal Fixtures (32 EA) - 16 EA are billable | 4500
REPLACE HAND HOLE COVER
|  |  | Quantity | Price (EA) | Extended Price
| Belvedere |  | 1 | 40 | 40
| Corte Madera |  | 11 | 40 | 440
| Fairfax |  | 5 | 40 | 200
| Larkspur |  | 6 | 40 | 240
| Marin County |  | 17 | 0 | 0 | Sched. 2 - Free
| Mill Valley |  | 5 | 40 | 200
| Novato |  | 52 | 0 | 0 | Sched. 2 - Free | [47 empty] | Sched. 2 - Free (We will honor these even though Sch. 1 now)
| San Anselmo |  | 3 | 40 | 120
| San Rafael |  | 28 | 40 | 1120
| San Rafael Pkg Lots |  | 1 | 40 | 40
| Sausalito |  | 6 | 40 | 240
| Tiburon |  | 5 | 0 | 0 | Sched. 2 - Free
|  |  | 140 | Total | 2640 | [48 empty] | SubTotal Hand Hole Covers (66 EA) | 2640
|  |  | 66 | Billable
[54 empty] | Total | 62740